## Sheet1
| Project Name | Project Duration | Project Start Date | Project End Date
| How AI is used in racing games? | 97 | 2020-01-23 | 2020-04-29
Task ID | Task Description | Task Duration | Start Date | End Date | 2020-01-23 | 2020-01-24 | 2020-01-25 | 2020-01-26 | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | 2020-02-01 | 2020-02-02 | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | 2020-02-08 | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | 2020-02-15 | 2020-02-16 | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | 2020-03-14 | 2020-03-15 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-21 | 2020-03-22 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-28 | 2020-03-29 | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09
1 | Proposal | 8 | 2020-01-23 | 2020-01-31 | X | X | X | X | X | X | X | X | X
2 | Research | 7 | 2020-02-01 | 2020-02-08 | [9 empty] | X | X | X | X | X | X | X | X
3 | Create Race Track | 4 | 2020-02-09 | 2020-02-13 | [17 empty] | X | X | X | X | X
4 | Create Player | 5 | 2020-02-14 | 2020-02-19 | [22 empty] | X | X | X | X | X | X
5 | Create AI Player | 7 | 2020-02-20 | 2020-02-27 | [28 empty] | X | X | X | X | X | X | X | X
6 | Programme AI Route | 7 | 2020-02-28 | 2020-03-06 | [36 empty] | X | X | X | X | X | X | X | X
7 | AI Overtake oposition | 7 | 2020-03-07 | 2020-03-14 | [44 empty] | X | X | X | X | X | X | X | X
8 | Collisions | 5 | 2020-03-15 | 2020-03-20 | [52 empty] | X | X | X | X | X | X
9 | Player Respawn | 5 | 2020-03-21 | 2020-03-26 | [58 empty] | X | X | X | X | X | X
10 | Game HUD | 7 | 2020-03-27 | 2020-04-03 | [64 empty] | X | X | X | X | X | X | X | X
11 | Win State | 7 | 2020-04-04 | 2020-04-11 | [72 empty] | X | X | X | X | X | X | X | X
12 | Create Main Menu | 5 | 2020-04-12 | 2020-04-17 | [80 empty] | X | X | X | X | X | X
13 | Game Testing | 3 | 2020-04-18 | 2020-04-21 | [86 empty] | X | X | X | X
14 | Game Improvements | 7 | 2020-04-22 | 2020-04-29 | [90 empty] | X | X | X | X | X | X | X | X
15 | Project Diary/Report | 91 | 2020-01-31 | 2020-05-01 | [8 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
16 | Polish | 7 | 2020-04-29 | 2020-05-06 | [97 empty] | X | X | X | X | X | X | X | X
17 | Submission | 1 | 2020-05-07 | 2020-05-08 | [105 empty] | X | X
Formulas:
Project Start Date = [Project End Date, row above]+1
Project End Date = [Project Start Date]+[Project Duration]